## Overview_Scope
IP Name | I2C
Scope | Covers register access validation and I2C0<->I2C1 DMA-based transfers in HS and Standard modes.
Out of Scope | Electrical characterization, third-party device interoperability beyond internal I2C0/I2C1.
Generated (IST) | 2026-04-27 21:01:15 IST
Source Directory | https://github.com/titusbspgit/PSVValidation/tree/main/TestRepo/i2c

## Assumptions
Assumptions
On-chip I2C0 (master) and I2C1 (slave) available on board.
Pull-ups sized appropriately (e.g., 4.7k) for target speeds.
DMA engine functional and accessible to I2C controller.
Clocks and resets configured; no other master contending the bus.

## Environment_Dependencies
Item | Detail
Board | PSV Platform
OS/FW | Linux/Baremetal (as applicable)
Kernel/Driver | I2C + DMA drivers loaded/enabled
Tools | Register access tool; log capture
Connections | I2C0<->I2C1 wired; UART for logs

## Test_Cases
ID | Name | Objective | Preconditions | Setup | Steps | Expected Results | Pass/Fail Criteria | Logs/Artifacts | Links
I2C_TC_001 | i2c_reg_rd_wr_test | Validate I2C IP register read/write accessibility and correctness across key registers and boundary addresses. | Board powered; PSV platform booted; I2C clocks enabled; Access permissions to I2C registers. | Ensure pull-ups present on SDA/SCL; Load low-level access utility/driver; Reset I2C IP to known state. | 1) Read default values; 2) Write test patterns to RW regs; 3) Read-back and compare; 4) Write-to-RO (expect no change); 5) Soft reset and re-verify defaults. | All RW registers read-back match writes; RO regs unchanged; Status/interrupt bits behave per spec. | PASS if all comparisons succeed and no bus errors/timeouts; else FAIL. | Console/UART logs; register dump CSV. | https://github.com/titusbspgit/PSVValidation/tree/main/TestRepo/i2c/i2c_reg_rd_wr_test
I2C_TC_002 | test_i2c0_mst_i2c1_slv_dma_hs_md | Validate HS-mode (3.4MHz) data transfers using DMA with I2C0 as Master and I2C1 as Slave. | I2C0 and I2C1 wired; HS-capable pull-ups; DMA engine enabled; Proper board power/clocking. | Configure I2C0 Master HS mode; I2C1 Slave address; Configure DMA channels and descriptors; Allocate buffers. | 1) Program HS mode on I2C0; 2) Arm I2C1 slave; 3) Start DMA TX from memory via I2C0 to I2C1; 4) Verify RX buffer; 5) Repeat with varying sizes and addresses. | No NACK/timeouts; Data integrity preserved (CRC/byte compare matches). | PASS if all transfers succeed with zero data mismatches and no HW errors; else FAIL. | DMA/I2C driver logs; buffer hexdumps; timing stats. | https://github.com/titusbspgit/PSVValidation/tree/main/TestRepo/i2c/test_i2c0_mst_i2c1_slv_dma_hs_md
I2C_TC_003 | test_i2c0_mst_i2c1_slv_dma_st_md | Validate Standard-mode (100kHz) data transfers using DMA with I2C0 as Master and I2C1 as Slave. | I2C0 and I2C1 wired; Standard-mode pull-ups; DMA engine enabled. | Configure I2C0 Master Standard mode; I2C1 Slave address; Setup DMA; Allocate buffers. | 1) Program Standard mode on I2C0; 2) Arm I2C1 slave; 3) Start DMA TX; 4) Verify RX buffer; 5) Try varied payload sizes and repeated starts. | Stable transfers; No arbitration loss; Data integrity OK. | PASS if integrity and error-free operation across matrix; else FAIL. | Driver logs; buffer comparisons. | https://github.com/titusbspgit/PSVValidation/tree/main/TestRepo/i2c/test_i2c0_mst_i2c1_slv_dma_st_md

## Traceability_Mapping
Requirement/Feature | Test Case IDs
Register accessibility (R/W/RO) | I2C_TC_001
DMA-based transfers | I2C_TC_002, I2C_TC_003
High-Speed mode operation | I2C_TC_002
Standard mode operation | I2C_TC_003
Master-Slave role correctness | I2C_TC_002, I2C_TC_003

## Execution_Matrix
Test ID | Mode | Payload Sizes | Runs | Result
I2C_TC_001 | N/A | N/A | 1 | TBD
I2C_TC_002 | HS (3.4MHz) | 64B, 256B, 1KB | 3 each | TBD
I2C_TC_003 | Standard (100kHz) | 64B, 256B, 1KB | 3 each | TBD

## Risks
Risk | Impact | Mitigation
HS timing margins insufficient | Data errors | Use proper pull-ups; verify clock config
DMA misconfiguration | Transfer failures | Use validated descriptors; sanity tests
Bus contention/locks | Timeouts | Ensure exclusive access; bus recovery